## Sheet1
Daily Front-End Project Update Template
Date | Seal, Corey & Bir Inder | Tasks Completed Today | HTML/CSS/Bootstrap Components Implemented | Graphics / Assets Added | Screenshots / Links | Issues / Blockers | Next Steps / Planned Tasks | Completion %
2025-10-14 | Corey | Designed wireframe and color for homepage hero section | Navbar, Hero section, responsive grid | NONE | https://github.com/sealubong2006/Bean-and-Brew.git | None | Designing next part of site | 85%
2025-10-14 | Bir Inder | Implemented Wireframe Design from Corey | Navbar, Hero section, responsive grid | Background Image, Icon for Account and logo | https://github.com/sealubong2006/Bean-and-Brew.git | Had some responsive issues but has been fixed | Menu and other components for front end | 95%
| Seal | Supervision and fixing complex issues that came up | Mobile Responsiveness | None | https://github.com/sealubong2006/Bean-and-Brew.git | None | Designing a footer for the page | 50%